## Slide 1
THEORY OF CHANGE
PRACTICAL GUIDE
Notes: Change to our cover

## Slide 2
TABLE OF CONTENTS
01
Introduction 3
02
What is a Theory of Change? 5
03
Why is ToC useful for climate change adaptation projects? 8
04
How do you start developing a ToC? 11
05
Leadership and participation 14
06
Describe the problem 17
07
Map a pathway of change 20
08
Define interventions 23
09
Identifying assumptions and barriers 25
10
Identify indicators and thresholds 28
11
The Diagram 30
12
Conclusions 32
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein 2021-1-IE01-KA220-ADU-000033706
13
Theory of Change - Glossary Terms & Abbreviations 34
Be sure to check out of Annex resources to start your own Theory of Change journey.
Notes: Keep

## Slide 3
01
INTRODUCTION

## Slide 4
Theory of Change (ToC) has become a common buzzword in climate adaptation circles in recent years, but it’s preparation can sometimes feel like yet another hurdle to overcome especially for small communities where resources are limited, and staff are often overstretched.
But for communities striving to become Climate Change Champions and prevent biodiversity loss, Theory of Change as a process could be a very powerful tool. In this document, we put the spotlight on ToC and why does it matter? What does ToC mean anyway, and how to start developing one?
In this Practical Guide we will highlight some of the most common features of ToC and examine how, if used appropriately, it can be a useful tool for Climate Change Champions Communities in planning and developing climate change projects. In doing so, we hope to demystify ToC and the jargon which often surrounds it. In our conclusions, we reinforce some key messages for those developing ToC for climate adaptation projects. We have also included a useful Glossary of terms and abbreviations at the end of this guide to help you navigate through the various terminology.
4
For a quick and easy start of the process of Theory of change development you may also check:
CLICK TO VIEW
01
INTRODUCTION

## Slide 5
02
WHAT IS A THEORY
OF CHANGE?

## Slide 6
One of the greatest challenges for practitioners is that there is no single definition for theory of Change (ToC), it can mean different things to different people. Consequently, expectations about how it should be used also differ.
So, let us start with where there is agreement. There is broad consensus in ToC literature that it is a planning process which articulates how change can be achieved. It begins by defining the long-term goal or vision statement (‘the change we want to happen’) and works backwards to systematically laying out each step along a ‘causal pathway’ – a series of steps which lead towards the long-term goal.
02
WHAT IS A THEORY
OF CHANGE?
A roadmap as it helps in defining a ‘destination’, how you expect to get there, the challenges
That may be faced and assumptions made about the nature of the journey. Critically, it also
Acknowledges that, like any journey, you may face unexpected challenges and need to
Reroute. This is consistent with adaptation planning which is often described as an iterative
Process where continual adjustment is required.
For many people, ‘Theory of Change’ is not a very helpful term; it sounds academic (theoretical) and vague. Because of this ToC is often rephrased. It is sometimes described as:
01
02
03
04
05

## Slide 7
USEFUL DEFINITIONS OF THEORY OF CHANGE
“Essentially an explanation of how
a group of stakeholders expects to reach
a commonly understood long-term goal”
(Anderson, 2005)
“The theory of change approach is a process of project
planning and evaluation which maps the relationship
between a long-term goal of a project and the
intermediate and early changes that are required to bring
it about. It encourages a project team or group of
stakeholders to explain how the project is understood to
reach its goals, and the process through which changes
will occur. The approach emphasizes the theory and
assumptions underlying the pathway of change from the
implementation of selected interventions and activities to
intended outcomes.”
(Conservation International, 2013)
Notes: Quotation slide 2

## Slide 8
Click to type
03
WHY IS ToC USEFUL FOR
ADAPTATION PROJECTS?
FOR CLIMATE CHANGE

## Slide 9
ToC is well suited to complex, multifaceted and long-term issues as it helps the user to focus on the question “how do I make change happen?” rather than “what should my project do?”
It can help us avoid falling into the trap of designing activities we are familiar with rather than those most relevant to the change we want to achieve. For example, we often consider workshops as a means of stakeholder engagement. Yet if a desired outcome is to “sustain ongoing awareness of climate and biodiversity related risks in communities” then a range of alternative activities might be considered such as training and upskill community champions to be positioned to create immediate social impact.
9
There are number of other reasons turning ToC into useful tool for climate adaptation planning:
03
WHY IS ToC USEFUL FOR
ADAPTATION PROJECTS?
FOR CLIMATE CHANGE
ToC encourages contextual analysis - how can change happen in a given location, sector or social group, what are the barriers and assumptions in this context – which is consistent with adaptation planning. Climate change is a global issue but adaptation is context specific.
01
02
ToC can connect diverse projects and programmes and enhance linkages across Climate Change Adaptation (CCA) sectors and scales. This is valuable given the multisector nature of adaptation and the growing array of adaptation investments being made to prevent biodiversity loss.

## Slide 10
10
ToC is designed to be iterative and flexible and allows projects to respond to changes in the social, political, or natural environment. This is vital for adaptation programmes, which need to accommodate dynamic and emerging conditions. This makes ToC a valuable tool for monitoring and evaluation (M&E) as well as adaptation planning.
03
04
There is a strong focus on the assumptions that underlie a programme and thresholds that identify what is needed to advance towards the desired change. This provides valuable markers against which the process can be assessed (and where necessary, adjustments to strategic direction made).
06
By discussing the underlying logic and the change stakeholders wish to see, different views and perspectives are revealed at an early stage. This helps to establish shared expectations which can avoid misunderstandings.
ToC can be a valuable monitoring and evaluation tool. Due to the long-term nature of climate change, it can be difficult to determine whether outcomes are achieved. ToC provides means of identifying ‘lessons learned’, which is a crucial way to build the evidence base on
climate change adaptation.
07
08
The flexible nature of ToC can better account for uncertainties that are inherent in adaptation processes. By monitoring assumptions ToC is agile and provides evidence of where changes may be needed at key points in the project process.
Being used as part of project or programme planning with stakeholders it can encourage a more open dialogue regarding perspectives and values, leading to a shared vision and stronger relationships with partners and stakeholders.
05
the jargon and quasi-academic terminology applied to ToC (including the term itself) and
people not knowing where to start. We will try to address these issues in the remainder of this Practical Guide.
01
02
On this basis, ToC would appear to be a valuable approach for those working on climate adaptation issues, yet it is often greeted by confusion and frustration. There are two main reasons for this

## Slide 11
Click to type
04
HOW DO YOU START
DEVELOPING A ToC?

## Slide 12
The key to developing a good ToC is to start simple and from the over-arching vision statement or change that you wish to see. Knowing who to involve and when is also essential.
Do not jump on immediately to developing the diagram, this will be a much easier task if you have prepared well and invested time in the process. If possible, use a facilitator with experience of ToC when discussing it in a group context. The facilitator will be able to guide you through the steps and provide a critical eye without getting lost in the content.
The steps in Figure 1 are explained in greater detail below, along with an example to illustrate the steps in practical terms.
04
HOW DO YOU START
DEVELOPING A ToC?
The key is to ‘start simple’’.
Figure 1 Steps in developing a Theory of Change
Getting Started – Leadership & Participation
01
Describe the problem
02
Pathway of change (incl. ‘ultimate objectives’)
03
Define interventions/activities
04
Articulate assumptions and barriers
05
Agree indicators and thresholds
06
ToC Diagram and Narrative

## Slide 13
Here is the first task for you to try and think of an example which might fit into your communities, following some of the good practices presented.
Task 1
Just for illustration we use a hypothetical community-level coastal resilience project in a small island nation comprising a mix of atolls and low-lying islands.
This project is looking to increase resilience in 20 communities which are highly exposed to direct and indirect impacts of climate change, including coastal inundation and flooding, coastal erosion and saline intrusion, biodiversity loss, loss of livelihoods and climate-related disasters such as cyclones

## Slide 14
05
LEADERSHIP &
PARTICIPATION

## Slide 15
The best theories of change are developed in a group involving different stakeholders. This provides alternative perspectives on the problem, the possible responses, definitions of success and assumptions.
By revealing differences in views, it can lead to a genuinely shared vision of where you want to go with your project and what is required to get there. However, it can be expensive and unwieldy to involve too many people at all stages, so compromises often need to be found. You will therefore need to think of who to involve and when. For example, you may decide to have a core group to develop the ToC with broad representation, then involve a wider group to examine and test the draft ToC at a particular point. Leadership is of utmost importance – consider carefully who will lead and coordinate this process.
As the ToC develops, the strategy for engagement of stakeholders the mapping table will need to be amended and updated regularly
05
By involving a variety of stakeholders,
it will be possible to dig deeper into the questions of ‘What change, for whom, why – and who says so?’
VIEWING THE WORLD DIFFERENTLY…
05
LEADERSHIP &
PARTICIPATION

## Slide 16
Mapping the Stakeholders
Task 2
То map the respective stakeholders use the stakeholder mapping table (Annex 1). It is important to consider which national/regional/local authorities will take a leading role and how to involve communities from the design stage onwards.
This should include identifying who can best represent different community groups and when, and how, to involve them. We should also consider consultation fatigue; a balance needs to be struck between positive engagement and over-consultation. This includes being sensitive to the many commitments of stakeholders.

## Slide 17
06
DESCRIBE THE PROBLEM
(SITUATION ANALYSIS)

## Slide 18
Understanding the problem(s) is a critical part of developing a ToC. This stage provides the rationale for change. In case everything is working perfectly and conditions are entirely stable there would be no need to do anything.
If the proposed solutions don’t address the root causes of the problems, our work will fail to affect the change we wish to see, so we really need to start with a sound understanding of the situation and the problem. Studying the problem can involve reviewing previous policies, research, vulnerability assessments and other sources of information. You will rarely, if ever, be starting this process from scratch, but it will require some synthesis of information and, in some cases, updating.
For example, you may have a document that summarises the main climate change impacts for the community/territory/settlement, but this work does not reflect the latest science. It is unlikely that the existing projections to be incorporated. Once you have studied the problem, you need to describe it briefly and clearly, backed up with evidence. This should be easy to understand and can be used when engaging stakeholders. It will form an important part of the rationale for any project proposal.
06
DESCRIBE THE PROBLEM
(SITUATION ANALYSIS)
It is worth remembering a ‘problem’ does not have to be a negative, for example, the‘problem’ may be that an intervention is working well but there is a lack of capacity to scale it up so that more people can benefit.

## Slide 19
Describe briefly the problems related climate change and biodiversity loss in the examples selected
Task 3
In the hypothetical example are described the problems which coastal communities currently face and the challenges which climate change will generate in the future. The situation analysis should draw upon existing evidence including climate science, risk and vulnerability assessments (who is most vulnerable to what and how) and related to this, the socio-economic situation at national and community level (for example the breadth of the economic base, employment and income data).
The climate rationale (how the project relates and responds to climate change challenges) needs to be clearly articulated and linkages to non-climate drivers identified. In this case, sea level rise, storm surge, rainfall intensity and sea surface temperatures might all be considerations. Other environmental stressors should also be considered (agricultural run-off, deforestation, over-fishing) and the socio-economic drivers of these stressors are also important to record. Gender and cultural factors need to be considered, especially in terms of roles, responsibilities and access to opportunities at household level.
Examples developed by Climate Champions project you find in Annex 2.

## Slide 20
07
MAP A PATHWAY
OF CHANGE

## Slide 21
A pathway of change (sometimes called an ‘outcomes pathway’, ‘impact pathway’, ‘outcomes chain’ or ‘casual pathway’) illustrates the assumed cause-and-effect relationships between the long-term goal, penultimate, intermediate and early outcomes.
This pathway is central to the rationale for the choice of activities, the justification of resources and the development of indicators. There are a number of ways to develop a pathway of change, but ToC usually involves backwards mapping, i.e. working backwards from a ‘big picture or ultimate outcome’ then identifying the objectives that will get you there. These outcomes can also be considered ‘preconditions’ (things that need be in place to make the next outcome possible or more likely).
An easy way to map backwards is to start with the ultimate outcome or change you wish to see. Ask yourself (or your group) “in order for this to happen what needs to be in place?”.
These will form your next level of outcomes. For these outcomes ask again: “in order for this to happen what needs to be in place?” and so on. A good way to test your pathway of change is to read it ‘ forwards’ i.e. from early outcomes to ultimate outcome, inserting the phrase “if then” between outcome levels.
This should flow logically, showing that if one outcome is achieved it is reasonably logical that the next is attainable. Once you have mapped out your outcomes and preconditions you may wish to group them under particular themes. This should not disrupt the flow between outcomes but may provide greater clarity when communicating the outcomes of the project to different groups.
MAP A PATHWAY
OF CHANGE
Results, products, goods or services which result from an intervention. (e.g. community map and report outlining stakeholder priorities produced)
The likely or achieved effects (results) of an intervention’s outputs. (e.g. adaptation actions implemented reflect stakeholder )
OUTPUTS
OUTCOMES
Tip to define activities and respective outputs and outcomes
Actions undertaken which help achieve outputs and outcomes (e.g. community takeholder workshop held)
ACTIVITIES
07

## Slide 22
Define the outcome or change you wish to see
Task 4
For the hypothetical example used – coastal resilience project, a possible change we wish to see is at household and community level therefore at the broadest level an overarching outcome could be that “coastal communities on the six most populated islands are more resilient to climate change”. However, this is a very general statement; we need to break this down into more specific outcomes. To do this we need to understand what resilience means to local communities, which vulnerabilities we are seeking to address, and which people are we aiming to support and involve?
Examples developed by Climate Champions project you find in Annex 2.
Develop a pathway in group
Task 5
Setting out your pathway of change on pieces of card can be a great group exercise as in enables you to re-order and adjust your ideas. Use cards with “in order for this to happen…”written on them and place them in between your outcomes/preconditions to test the flow of your ideas.
You can also add in some interventions, assumptions and indicators (see the respective steps) on cards to build up a more complete ToC. This can also be a fun exercise which increases understanding on the process of developing a ToC.
You may wish to start with a warmup exercise by developing a simple pathway of change for a daily activity such as ‘getting to work on time’. This always helps people to understand the logic of the approach before dealing with more complex climate change-related tasks.
ToC can help us to answer such questions. In mapping out the project using our ToC we should aim to address the underlying factors which lead to vulnerability to climate change – i.e. tackling the problems not just the symptoms. In this example, the pathway of change might consider physical resilience to climate-related disasters but also socio-economic resilience, for example in response to reduced income from inshore fisheries due to reef degradation.

## Slide 23
08
DEFINE INTERVENTIONS

## Slide 24
Once you understand how your intermediate outcomes contribute to your ultimate outcome and vision you can begin to consider the activities or interventions that can help to achieve each outcome. Having already developed a pathway of change it is easier to ensure that your interventions are targeted towards the change you wish to see.
Perhaps because we have a natural tendency towards “getting on with things” there is a tendency amongst some project planners to start with interventions rather than outcomes. This can mean that we do not think clearly how the intervention will help us meet our short, medium and long-term objectives. This can mean than interventions lack focus or are not placed in the correct sequence.
This is particularly important when engaging stakeholders and communities. For example, there is little point in investing in a detailed appraisal of an adaptation option which is not acceptable to stakeholders. Equally, communities may be best placed to provide feedback on an option once the concept has been sufficiently developed and some aspects of feasibility can be reported back.
08
DEFINE INTERVENTIONS
Think of possible interventions to achieve the desired outcome of your project
Task 6
The interventions will depend on the situation analysis, how resilience is defined and the outcomes we wish the project to achieve. We should consider where and what type of change is required to achieve our desired outcomes. This could range from strengthening national policies to behaviour changes at household level.
Timescales should also be taken into account; it may be important for communities to see some short-term benefits as well as considering long term impacts and responses.
In our example project, we may decide that mangrove restoration is a valuable intervention which can bring benefits in the short, medium and long term.
Examples developed by Climate Champions project you find in Annex 2.

## Slide 25
09
IDENTIFYING ASSUMPTIONS
& BARRIERS

## Slide 26
09
The assumptions we make (just about everything we do) are influenced by our personal values, professional experience, the evidence we are presented (Vogel 2012), our cultural background and many other factors.
The assumptions we make (just about everything we do) are influenced by our personal values, professional experience, the evidence we are presented (Vogel 2012), our cultural background and many other factors. It may not be immediately evident, but the pathway of change, interventions and indicators that you will develop will be shaped by assumptions about how change happens, and what and who in your group are important in affecting change. So, what has this got to do with designing a good Climate Change Community Champions project? If the assumptions we make about how outcomes will be achieved are wrong, then they become unstable steps on our pathway of change, just as if a road was blocked, we might find it impossible to reach our destination. Assumptions are time sensitive; we can’t know how circumstances may or may not change in the future so we have to make some realistic assumptions about what we think will happen, ideally backed up with evidence to justify them.
By clearly identifying your assumptions it is possible to test and monitor them. We might assume an intervention which worked on one island will work in another, but by testing this assumption with community leaders in the design phase project we may find that the activity is culturally appropriate in one place but not in another. As well as assumptions, it is also useful to list the barriers that you feel you will face in achieving each objective. This may lead to you revisiting and adjusting the proposed interventions.
IDENTIFYING ASSUMPTIONS
& BARRIERS
“Every programme is packed with beliefs, assumptions and hypotheses about how change happens – about the way humans work, or organisations, or political systems, or ecosystems. Theory of change is about articulating these many underlying assumptions about how change will happen in a programme.”
Rogers (2008)
ASSUMPTIONS

## Slide 27
Underline assumptions about how desired change will happen in your example, list possible barriers
Task 7
For example, we may assume that local communities recognise the importance of mangroves as a form of ecosystem-based adaptation because they have valued a previous mangrove restoration project nearby. However, if there is an unexpected economic shock, the same community may begin to destroy the mangrove for firewood.
If we are monitoring the assumptions we have made during the course of the project, we can spot where and when the assumptions are no longer valid. With this monitoring information, it may be possible to introduce activities to remediate problems within or outside of the project scope.
For example, we could increase economic diversification activities within the existing project or work with another project to improve the short-term economic situation for local people.
In turn, the evaluation of the project should highlight that, in this case, it cannot be assumed that communities will continue to value the longer-term ecosystems services created by mangrove restoration if they face greater short-term economic hardship scope.
Examples developed by Climate Champions project you find in Annex 2.

## Slide 28
10
IDENTIFY INDICATORS
& THRESHOLDS

## Slide 29
ToC is a valuable tool for monitoring and evaluation (M&E) of climate change adaptation as its inherent flexibility is well suited to long-term issues where uncertainties need to be acknowledged.
The overt recognition of underlying assumptions enables learning to be prioritised; it can help us to ask “what works, in which contexts and why?” This is especially important for climate change, where we are still learning what effective adaptation looks like. Too often, conventional project monitoring and evaluation (M&E) leads us towards questions such as “have we done what we said we would do?” which focuses strongly on accountability and can limit learning that might benefit future adaptation efforts. When considering M&E, it is important to remember that factors outside of a given project can contribute to the success (or not) of a project or programme. These should be considered when examining barriers.
Working in groups is the best way to identify indicators that demonstrate progress towards a specific a precondition/outcome or progress along a pathway of change. It should also be possible to identify thresholds. Thresholds are slightly different from indicators in that they identify the point at which an outcome is met. It is important to remember that ToC thresholds may be beyond the scope of what a single programme can achieve, whereas log frame result targets should be realistically within the reach of a project. Both indicators and thresholds will need to be discussed within your group as they are subjective.
10
IDENTIFY INDICATORS
& THRESHOLDS
identify indicators that demonstrate progress towards the outcomes defined for you example and the respective thresholds
Task 8
In coastal resilience example project, if one of our objectives is to “reduce losses from flooding and coastal inundation” should we define success as a) no losses at all (is this realistic?) b) a percentage reduction in losses, if so, by how much and for which farmers? Should we include noneconomic losses such as loss of knowledge or cultural value of land? Such discussions are closely linked to assumptions that underpin climate adaptation work – we all have different expectations of how change may happen and what success looks like. ToC can help expose and resolve these differences before and during implementation.
Examples developed by Climate Champions project you find in Annex 2

## Slide 30
11
THE DIAGRAM

## Slide 31
11
ToC is often discussed purely in terms of the end product – usually a diagram which illustrates the connections between interventions and outcomes, as well as the barriers and assumptions. If viewed purely as a diagram, the ToC is little more than a summary of interventions and outcomes
If it has been developed quickly, with limited engagement and at the end of the project or proposal development process, the benefits of ToC will not be realised. Ideally, a ToC diagram should be a summary of a detailed ToC process.
There is no single way to construct a ToC diagram but at a minimum it should clearly illustrate the ultimate outcome (the change we want to happen), the flow between outcomes/preconditions, how specific interventions support these outcomes, the key assumptions and the barriers that have been considered. Like all good diagrams, it should be clear, as simple as possible with a clear logic (remember, you can test the logical flow byplacing the phrase “in order for this to happen” between your outcomes). If more detail is required, include a narrative explanation of the diagram, including who was involved in developing it. This can help avoid an over-crowded or confusing diagram.
THE DIAGRAM
Follow the link below summarise the ToC development.
CLICK TO VIEW
Check Annex 3 for development of the logical model.

## Slide 32
12
CONCLUSIONS

## Slide 33
ToC can be a valuable project and programme design tool that also supports effective M&E.
In order for its potential to be fulfilled, it needs to be considered as a process (or even a way of thinking) rather than just as a product or diagram. It requires commitment and careful planning and should involve key stakeholders. The greatest strength of ToC is that it enables reflection and adjustment during the course of a project; effective ToC involves a tacit acknowledgement that the process of change rarely happens exactly as we plan it. Too often ToC is thrust upon ill-prepared, over-stretched project staff as a ‘donor requirement’ and therefore it becomes viewed as ‘management jargon’ or a hoop to jump through. Donors who promote the use of ToC as a flexible approach must reciprocate by showing flexibility in their approach to project M&E; if ToC reveals a change of direction or approach is needed, then such changes must be supported (and not blocked by bureaucracy). In short, for ToC to be truly useful, it requires an environment which values learning, appreciates complexity and supports adaptive management approaches. This responsibility falls upon those financing climate adaptation as well as those designing and implementing climate adaptation projects.
12
CONCLUSIONS
Keep it simple. Focus on getting the ultimate outcome right and work back from there using “in order for this to happen…” and “if then” logic.
Try not to get bogged down in the jargon. Use terminology such as ‘roadmap’, ‘project map’ or ‘story’ if people are confused by the terminology. Use the Jargon Buster if you are unsure.
Involve stakeholders, but keep it manageable. Establish a group who have the time to think this through and then have a plan to engage more widely later on.
Never present a ToC as a finished product. Conditions change, assumptions change, projects change…so your ToC should be a ‘living’ framework.
ToC should connect short-term actions to a ‘bigger picture’ of change we wish to see (the ultimate outcome). That said, avoid bold but vague vision statements as it can be hard to connect these to practical actions.
Focus on your assumptions. These are really important and help avoid individuals or groups becoming wedded to ideas or preconceptions.
Don’t dump your ToC once you get your funding. Remember, discarding your ToC is like forgetting your map on a long journey.
For those in the process of developing theories of change, remember:
01
02
03
04
05
06
07

## Slide 34
13
THEORY OF CHANGE -
GLOSSARY TERMS &
ABBREVIATIONS

## Slide 35
13
Assumptions:
What we assume about how change might happen (e.g. how the public will react to an idea, the affordability of an action etc). This can include assumptions aboutenvironmental and socio-economic conditions (scale of land use change, biodiversity loss, economic stability etc). Understanding assumptions is key to a good ToC process.
Backwards mapping:
Working backwards from a ‘big picture or ultimate outcome’ then identifying the objectives that will get you there in reverse chronological order. An easy way to map backwards is to start with the ultimate outcome or change you wish to see. Ask yourself (or your group) “in order for this to happen what needs to be in place?”.
Barriers:
Factors that may hinder the implementation of the project and which may disrupt the logic between outcomes, thus stalling or preventing change from happening. By recognising a barrier, either before or during a project, activities can be adjusted to mitigate this. An example of a barrier might be cultural resistance to change. When this barrier is identified more emphasis might be put on community sensitization and engagement or on engaging community leaders.
Indicator:
Indicators that demonstrate progress towards a specific a recondition/outcome or progress along a pathway of change. For example, an indicator of improved management of climate-related risks in the private sector might be the “percentage of businesses that have joined a climate impacts insurance scheme”.
Other useful definitions of indicators include:
“An indicator provides evidence that a certain condition exists or certain results have or have not been achieved and can be either quantitative or qualitative.” (Biesbroek and Swart 2014).
Indicators provide “clues and direction on how change is occurring and if outcomes are being achieved” (Climate-Eval Community of Practice, 2015).
“In order for this to happen…” and “if then” logic:
These are useful ways of testing your outcomes pathway. Working back from the ultimate outcome or change you wish to see, place the phrase “in order for this to happen…” between each precondition/outcome. You can also test your logic by reading ‘forwards’ i.e. from early outcomes to ultimate outcome, inserting the phrase “if then” between outcome levels. This should flow logically, showing that if one outcome is achieved it is reasonably logical that the next is attainable.
THEORY OF CHANGE -
GLOSSARY TERMS &
ABBREVIATIONS

## Slide 36
Outputs:
Results, products, goods or services which result from an intervention. For example, an intervention might be to hold a public consultation. The output could be that 200 people participated and were consulted on climate change adaptation options. The outcome (see below) might be greater community commitment to the selected adaptation option.
Outcome:
The likely or achieved effects (results) of an intervention’s outputs. These results occur after shorter term outputs are achieved and sometimes long after project activities are completed. Outcomes might relate to improved knowledge, attitudes, beliefs, skills, behaviours, access, policies and environmental conditions. In ToC, these outcomes can also be considered ‘preconditions’ (things that need be in place to make the next outcome
possible or more likely).
Ultimate outcome:
The high-level outcome you wish to achieve. This sits at the top of your ToC diagram (or just below the vision statement) and should articulate the main change(s) you wish to achieve.
Intermediate outcome:
An outcome which contributes to the achievement of your ultimate outcome and, as such, is a precondition for the ultimate outcome.
M&E:
monitoring and evaluation
Pathway of Change/Outcomes;
Pathway/Impact; Pathway/Outcome; Chain/Causal Pathway:
These closely-related terms are often used interchangeably and refer to a way of showing each outcome in its logical relationship to all the others, as well as chronological flow. These approaches illustrate the (assumed) cause-and-effect relationships between the long-term goal and the penultimate, intermediate and early outcomes.
Preconditions:
Conditions that need be in place to make the next outcome possible or more likely. A precondition is therefore an outcome for a nearer point in time.
Theory of Change (ToC): Variously defined but generally refers to a planning process which articulates how change can be achieved. Other definitions include “an explanation of how a group of stakeholders expects to reach a commonly understood long-term goal” (Anderson,2005) and “a process of project planning and evaluation which maps the relationship between a long-term goal of a project and the intermediate and early changes that are required to bring it about” (Conservation International, 2013).
Threshold:
A threshold is different from an indicator as it identifies the point at which an outcome is met. For example, an indicator of improved management of climate-related risks in the private sector might be the “percentage of businesses that have joined a climate impacts insurance scheme” but the threshold might be “75% of businesses have joined a climate impacts insurance scheme”. As such, a threshold requires discussion and agreement
on what constitutes success.
Vision statement:
An idealistic description of the desired outcomes achieved after successful completion of a project or programme. It is a vivid description that is designed to inspire the project beneficiaries, funders and those implementing the project.

## Slide 37
www.climatechampions.how
FOLLOW OUR JOURNEY
CLICK TO VIEW
Be inspired to be a Climate Champion in your community – check out our other resources:-
Communities in Action Compendium (inspiring best practice) – click here
Empowering Biodiversity and Climate Change Community Champions Course – click here